## Juanma1313-dys-issues
id	Title	Body	Created At	Updated At	Labels	milestone	State
12	USER STORY: Register an account	As **anonymous user**, I can **register myself**, so that **I can select my favourite content** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am an `Anonymous` user (non registered) **When** I am in the sign-in website page **Then** I can access the sign-up page following the `sign up` link - Acceptance Criteria 2 **Given** that I am an `Anonymous` user (non registered) **When** I am in any website page **Then** I can access the sign-up page selecting the sin-up option in the user menu - Acceptance Criteria 3 **Given** that I am a non `Anonymous` user (user already registered) **When** I am in the home page **Then** the `join us ...` link should not be available - Acceptance Criteria 4 **Given** that I am in the sign-up webpage **When** I have entered a valid e-mail address and a valid password **Then** The new account is created ## Tasks - [x] Task 1 - Adapt Django's allauth accounts application to allow user registration via email. - [x] Task 2 - Create the sign-up option menu in the user menu in the base template ## Story Points: 2 + 1 ## Epic: #38 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 02:51:18+00:00	2024-04-02 09:14:18+00:00	[Label(name="must have"), Label(name="3")]	Milestone(title="DIY Site Backlog", number=1)	open
13	USER STORY: Validate e-mail	As **user**, I can **validate my own e-mail**, so that **I can sign in the website** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a new `Registered` user **When** I have created an account using the sign-up webpage **Then** an e-mail validation is sent to the new account e-mail address **Then** we will be redirected to a webpage with instructions on how to verify the e-mail Address. - Acceptance Criteria 2 **Given** that I am a new `Registered` user that has received an e-mail verification e-mail **When** I follow the link contained in the e-mail verification e-mail **Then** I will be directed to the `confirm-Email` webpage - Acceptance Criteria 3 **Given** that I am a new `Registered` user redirected to the `confirm-Email` webpage **When** I click the confirm button **Then** the e-mail is confirmed **Then** I am redirected to the sign-in webpage ## Tasks - [x] Task 1 - Create an e-mail account for Django's automated e-mail (on Gmail, Yahoo, etc) - [x] Task 1 - Adapt Django's allauth accounts application to allow e-mail validation. ## Story Points: 2 + 1 ## Epic: #38 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 02:52:55+00:00	2024-04-02 09:15:13+00:00	[Label(name="must have"), Label(name="3")]	Milestone(title="DIY Site Backlog", number=1)	open
14	USER STORY: Sign in	As **user**, I can **sign on the website**, so that **I can mark my favourite content** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Registered` user not logged in **When** I am in any website page **Then** I can access the sign-in web page selecting the `sign in` option in the user menu - Acceptance Criteria 2 **Given** that I am a `Registered` user not logged in **When** I am in the home page **Then** I can access the sign-in web page following the `join us ...` link - Acceptance Criteria 3 **Given** that I am in the sign-in webpage **When** I have entered a valid e-mail address and a valid password **Then** I become logged in the website **Then** The user menu button should contain my username - Acceptance Criteria 4 **Given** that I am a user not logged in **When** I am in any website page **Then** The user menu button should contain `Anonymous` ## Tasks - [x] Task 1 - Adapt Django's allauth accounts application to allow user sign-in via email. - [x] Task 2 - Create the `sign in` option menu in the user menu in the base template ## Story Points: 2 + 1 ## Epic: #38 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 02:54:48+00:00	2024-04-02 09:27:18+00:00	[Label(name="must have"), Label(name="3")]	Milestone(title="DIY Site Backlog", number=1)	open
15	USER STORY: Change e-mail	As **user**, I can **change my own e-mail address**, so that **I can sign in on the website with new e-mail address** / --- / ## Acceptance Criteria / - Acceptance Criteria 1 / **Given** that I am a `Registered` user / **When** I am in any website page / **Then** I can access the E-mail web page selecting the `E-mail` option in the user menu / - Acceptance Criteria 2 / **Given** that I am in the e-mail webpage / **When** I fill the email field with a valid e-mail address and use the button `Add Email` / **Then** The e-mail address is added to user's list of addresses / - Acceptance Criteria 3 / **Given** that I am in the e-mail webpage and I have more than one e-mail addresses / **When** I select an e-mail address from the list and use the button `Make Primary` / **Then** The selected e-mail address will be the new `Primary` that will be used for sign-in / ## Tasks / - [x] Task 1 - Adapt Django's allauth accounts application to allow users to manage their e-mail addresses. / ## Story Points: / 1 / ## Epic: / #38 / ## Iteration: / [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 02:57:11+00:00	2024-04-02 09:42:11+00:00	[Label(name="must have"), Label(name="1")]	Milestone(title="DIY Site Backlog", number=1)	open
16	USER STORY: Delete own account	As **user**, I can **Delete my own account**, so that **I can erase my information from the website**	2024-03-28 02:59:35+00:00	2024-04-10 14:14:49+00:00	[Label(name="could have")]	Milestone(title="DIY Site Backlog", number=1)	open
17	USER STORY: Administrate users	As **Administrator**, I can **Create/modify/delete user accounts and their privileges**, so that **I can assign who signs in on the website and who can create or modify content** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am an `Administrator` user **When** I am in any website page **Then** I can access the admin web page selecting the `Admin` option in the user menu - Acceptance Criteria 2 **Given** that I am an `Administrator` user **When** I am in admin website page **Then** I can add/delete/modify any user - Acceptance Criteria 2 **Given** that I am an `Administrator` user **When** I am in admin website page **Then** I can add/delete/modify any user group - Acceptance Criteria 2 **Given** that I am an `Administrator` user **When** I am in admin website page **Then** I can add/delete/modify any privilege of any user and any group - Acceptance Criteria 3 **Given** that I am an `Administrator` user **When** I am in admin website page **Then** I can add/delete/modify any privilege of any user and any group ## Tasks - [x] Task 1 - Install and setup Django's allauth and its accounts and interfaces, extensions. - [x] Task 2 - Create at least one administrator account - [x] Task 3 - Customize allauth templates to the website base template - [x] Task 4 - Create `Content Creators` user group with necessary privileges for content creators ## Story Points: 3 + 1 + 3 + 1 ## Epic: #37 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 03:08:24+00:00	2024-04-10 10:03:22+00:00	[Label(name="must have"), Label(name="8")]	Milestone(title="DIY Site Backlog", number=1)	open
18	USER STORY: Reset/Change password	As **user**, I can **Reset and change my own password**, so that **I can recover my account if I forget my password or enforce security to my account** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am in the sign-in webpage **When** following the link `Forgot your password?' **Then** I get redirected to the Password/reset webpage - Acceptance Criteria 2 **Given** that I am in the Password/reset webpage **When** I fill my user e-mail address and use the `Reset My Password` button **Then** a password reset e-mail is sent to the e-mail address **Then** we will be redirected to a webpage with instructions on how to reset the password. - Acceptance Criteria 3 **Given** that I am a Registered user that has received a password reset e-mail **When** I follow the link contained in the password reset e-mail **Then** I will be redirected to the change password webpage - Acceptance Criteria 4 **Given** that I am a Registered user that has been redirected to the change password webpage **When** I fill in a valid password **Then** The account password will be changed to the new password **Then** I will be redirected to the change password done webpage ## Tasks - [x] Task 1 - Adapt Django's allauth accounts application to allow user password reset. ## Story Points: 1 ## Epic: #38 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 03:14:10+00:00	2024-04-04 09:06:41+00:00	[Label(name="must have"), Label(name="1")]	Milestone(title="DIY Site Backlog", number=1)	open
19	USER STORY: View list of published projects	As **user**, I can **view a list of published projects**, so that **I can choose what projects to view in detail** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a user **When** I am in any website page **Then** I can access the website home page clicking on the website logo or brand name - Acceptance Criteria 2 **Given** that I am a user **When** I am in the home website page **Then** I can view the list of all the published DIY Projects - Acceptance Criteria 3 **Given** The list of all the published DIY Projects is displayed **When** each DIY project is displayed **Then** The Title, featured pictured, author, published date and number of likes should be displayed - Acceptance Criteria 4 **Given** that I am a user **When** I select a DIY Projects from the DIY Project list **Then** I get redirected to the selected DIY Project details webpage ## Tasks - [x] Task 1 - Add a paginated list of DIY Published projects to the index template ## Story Points: 5 ## Epic: #41 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 03:19:47+00:00	2024-04-04 10:29:20+00:00	[Label(name="must have"), Label(name="5")]	Milestone(title="DIY Site Backlog", number=1)	open
20	USER STORY: View details of a DIY project	As **user**, I can **Access the details of the selected DIY project**, so that **I can view the components and the instructions** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a user **When** I am redirected to the DIY Project details website page **Then** I can view the DIY Project's Title, featured image, author, Published date, Description, number of components, number of Instructions, Number of likes, the components list and the Instructions list - Acceptance Criteria 2 **Given** that I am a user **When** viewing the components list **Then** I can see each component's title, featured image, and description - Acceptance Criteria 3 **Given** that I am a user **When** viewing the instructions list **Then** I can see each instruction's title, and its content ## Tasks - [x] Task 1 - Create the Django view and controllers to handle DIY details - [x] Task 2 - Create a template for the DIY Project details - [x] Task 3 - Add to the details template a presentation header with all the DIY Project details - [x] Task 4 - Add to the details template a list of the components related to the DIY Project - [x] Task 5 - Add to the details template a list of the instructions related to the DIY Project ## Story Points: 1+1+1+3+2 ## Epic: #41 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 03:24:27+00:00	2024-04-10 10:06:36+00:00	[Label(name="must have"), Label(name="8")]	Milestone(title="DIY Site Backlog", number=1)	open
21	USER STORY: View Components	As **user**, I can **select and view a project component**, so that **I can access the details of the component** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a user **When** in the DIY Project details webpage, and selecting a component from the components list **Then** if the component is also a DIY Project, I get redirected to this DIY Project detail website page ## Tasks - [x] Task 3 - In the DIY Project details template, add a link to its DIY project detail for all the components related to the DIY Project and are DIY Projects themselves. ## Story Points: 3 ## Epic: #41 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 03:31:10+00:00	2024-04-05 15:53:12+00:00	[Label(name="must have"), Label(name="3")]	Milestone(title="DIY Site Backlog", number=1)	open
22	USER STORY: Mark a project as favourite	As **a registered user**, I can **mark a project as favourite**, so that **I can keep a collection of favourite projects and the projects get rated** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a signed-in user **When** I am viewing a DIY Project details **Then** I can click on the favourite icon to toggle the current DIY Project as favourite for me. ## Tasks - [x] Task 1 - Modify the DIY Project class model to handle DIY likes. - [x] Task 2 - Create the Django view and controllers to handle DIY likes - [x] Task 3 - Modify DIY Project detail template to handle DIY likes ## Story Points: 2+2+1 ## Epic: #41 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 03:35:54+00:00	2024-04-10 10:08:04+00:00	[Label(name="must have"), Label(name="5")]	Milestone(title="DIY Site Backlog", number=1)	open
23	USER STORY: Create a DIY project	As **content creator**, I can **Create a DIY project**, so that **I can publish it and share it on the website** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am in any website page **Then** I can access the admin web page selecting the `Admin` option in the user menu - Acceptance Criteria 2 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am in admin website page **Then** I can create a new DIY Project - Acceptance Criteria 3 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I have created a new DIY Project **Then** The Created date, Modified_Date and Parent fields are automatically created for this DIY project ## Tasks - [x] Task 1 - Allow the `Admin` option menu in the user menu in the base template for Staff users (from group `Content Creators`) - [x] Task 2 - Create at least one user from the `Content Creator` user group and the `Staff` flag enabled - [x] Task 3 - Create the DIY Project object model (`Thing`) that will be used to instantiate each `Thing` and each `Component` - [x] Task 4 - Create the Admin view for the DIY Project (`ThingAdmin`) ## Story Points: 1 + 1 + 6 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 03:38:45+00:00	2024-04-10 13:47:23+00:00	[Label(name="must have"), Label(name="8")]	Milestone(title="DIY Site Backlog", number=1)	open
24	USER STORY: Create DIY project details	As **content creator**, I can **create the DIY project details**, so that **project can have a featured image and description** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I have created a new DIY Project (`Thing`) **Then** I can assign a Title, Author, Status, and Featured Image - Acceptance Criteria 2 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I have created a new DIY Project (`Thing`) **Then** I can edit a WSWG document to the description - Acceptance Criteria 3 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I have created a new DIY Project (`Thing`) **Then** Slug field should be assign/updated automatically. - Acceptance Criteria 4 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I have created a new DIY Project (`Thing`) **Then** I need to use a Save button to permanently store the changes in the database ## Tasks - [x] Task 1 - Install Django Summernote extension for adding embedded WSWG editing functionality. - [x] Task 2 - Modify the DIY Project Admin view (`ThingAdmin`) to accommodate all detail fields - [x] Task 3 - Add the modifiable fields to the fieldsets in the DIY Project Admin view (`ThingAdmin`) to allow updating of these fields. ## Story Points: 3 + 5 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 03:52:39+00:00	2024-04-10 13:45:46+00:00	[Label(name="must have"), Label(name="8")]	Milestone(title="DIY Site Backlog", number=1)	open
25	USER STORY: Create Instructions	As **content creator**, I can **create a list of project instructions**, so that **the users can read and follow them** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (`Thing`) **Then** I can create a new `instructions` element that will be automatically assigned to the current DIY Project ## Tasks - [x] Task 1 - Create the DIY Instructions class model (`Instructions`) that will be used to instantiate each `instructions` object - [x] Task 2 - Modify the DIY Project object model 'Thing' to include the instructions model - [x] Task 2 - Create the DIY Component Admin view (`InstructionsInLine`) to handle new instructions elements as a list. - [x] Task 3 - Add inline admin view `InstructionsInLine` to the DIY Project Admin view (`ThingAdmin`) to allow new instructions elements to be added as a list. ## Story Points: 1+1+2+1 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 03:57:02+00:00	2024-04-10 09:54:20+00:00	[Label(name="must have"), Label(name="5")]	Milestone(title="DIY Site Backlog", number=1)	open
26	USER STORY: Create component	As **content creator**, I can **create a list of components**, so that **a user can view and gather the building blocks to fulfil the project** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (`Thing`) **Then** I can create a new component that will be automatically assigned to the current DIY Project ## Tasks - [x] Task 1 - Modify the DIY Project object model 'Thing' to include a relation to itself as `components` - [x] Task 1 - Create the DIY Component Admin view (`ComponentInLine`) to handle new components as a list. - [x] Task 2 - Add inline admin view `ComponentInLine` to the DIY Component Admin view (`ComponentInLine`) to allow new components to be added as a list. ## Story Points: 1+2+2 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 04:02:48+00:00	2024-04-10 10:00:35+00:00	[Label(name="must have"), Label(name="5")]	Milestone(title="DIY Site Backlog", number=1)	open
27	USER STORY: Modify a project details	As **content creator**, I can **modify the DIY project details**, so that **the project can be corrected or upgraded** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (Thing) **Then** I can change the Title, Author, Status, and Featured Image - Acceptance Criteria 2 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (Thing) **Then** I can edit a WSWG document to the description ## Tasks - Built in #24 ## Story Points: 0 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 04:05:41+00:00	2024-04-10 13:39:48+00:00	[Label(name="must have"), Label(name="0")]	Milestone(title="DIY Site Backlog", number=1)	open
28	USER STORY: Modify component	As **content creator**, I can **modify the component details**, so that **the component can be corrected or upgraded** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (`Thing`) **Then** I can change the title of the Instructions element - Acceptance Criteria 2 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (`Thing`) **Then** I can change the content of Instructions with a WSWG built-in editor - Acceptance Criteria **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (`Thing`) **Then** I need to use a `Save` button to permanently store the changes in the database ## Tasks - built in #24 - [x] Task 1 - Add Summernote edit functionality to the `description` field in inline DIY Component Admin view (`ComponentInLine') to allow for the WSWG edit features in the DIY Component list. - [x] Task 4 - Add the modifiable fields to the fieldsets in the inline DIY Component Admin view (`ComponentInLine`) to allow updating of these fields. ## Story Points: 2+1 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 04:07:34+00:00	2024-04-10 13:31:08+00:00	[Label(name="must have"), Label(name="3")]	Milestone(title="DIY Site Backlog", number=1)	open
29	USER STORY: Modify instructions	As **content creator**, I can **modify the project instructions**, so that **the project can be corrected or upgraded** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (`Thing`) **Then** I can change the title of the Instructions element - Acceptance Criteria 2 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (`Thing`) **Then** I can change the content of Instructions with a WSWG built-in editor - Acceptance Criteria **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (`Thing`) **Then** I need to use a `Save` button to permanently store the changes in the database ## Tasks - [x] Task 1 - Add Summernote edit functionality to the `instructions` field in DIY Instructions Admin view (`InstructionsAdmin') to allow for the WSWG edit features. - [x] Task 2 - Add the `title` and `instructions` fields to the fieldsets in the DIY Instructions Admin view (`InstructionsAdmin`) to allow updating of these fields. - [x] Task 3 - Add Summernote edit functionality to the `instructions` field in inline DIY Instructions Admin view (`InstructionsInLine') to allow for the WSWG edit features in the DIY Project Details Instructions list. - [x] Task 4 - Add the `title` and `instructions` fields to the fieldsets in the inline DIY Instructions Admin view (`InstructionsInLine`) to allow updating of these fields. ## Story Points: 2+1+1+1 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 04:08:29+00:00	2024-04-10 13:13:41+00:00	[Label(name="must have"), Label(name="5")]	Milestone(title="DIY Site Backlog", number=1)	open
30	USER STORY: Delete a project	As **content creator**, I can **delete a DIY project**, so that **the project does no longer exist on the website** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I select a DIY project from the DIY Projects list in the admin website page **Then** I can delete all the selected projects - Acceptance Criteria 2 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project in admin website page **Then** I can delete the current DIY Project - Acceptance Criteria 3 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I have requested to delete one or more DIY projects **Then** I will have to explicitly confirm the deletion ## Tasks Built in #23 ## Story Points: 0 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 04:10:10+00:00	2024-04-10 10:49:27+00:00	[Label(name="must have"), Label(name="0")]	Milestone(title="DIY Site Backlog", number=1)	open
31	USER STORY: Delete component	As **content creator**, I can **delete a component**, so that **the component does no longer exist on the website** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (`Thing`) **Then** I can delete an existing DIY Component from the current DIY Project - Acceptance Criteria 2 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I have requested to delete one or more DIY Components **Then** I will have to explicitly confirm the deletion ## Tasks Built in #26 ## Story Points: 0 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 04:11:10+00:00	2024-04-10 10:53:14+00:00	[Label(name="must have"), Label(name="0")]	Milestone(title="DIY Site Backlog", number=1)	open
32	USER STORY: Delete Instructions	As **content creator**, I can **delete project instructions**, so that **those instructions do no longer exist on the website** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I am modifying a DIY Project (`Thing`) **Then** I can delete an existing Instructions element from the current DIY Project - Acceptance Criteria 2 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I have requested to delete one or more Instructions elements **Then** I will have to explicitly confirm the deletion ## Tasks Built in #25 ## Story Points: 0 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 04:12:57+00:00	2024-04-10 10:52:24+00:00	[Label(name="must have"), Label(name="0")]	Milestone(title="DIY Site Backlog", number=1)	open
33	USER STORY: Change project Published status	As **content creator**, I can **change a project published status **, so that **the project is available to users when marked as published or hidden when it is marked as draft** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I have selected one or more DIY Projects from the DIY projects list **Then** I can toggle the published flag `Status` so that the DIY Project can be shown or hidden from viewing users. ## Tasks - [x] Task 1 - Modify the DIY Project Admin view (`ThingAdmin`) to update the `status` field - [x] Task 2 - Add `publish` and `set_as_draft` actions to the DIY Project Admin view ## Story Points: 2 + 3 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 04:16:55+00:00	2024-04-10 09:19:12+00:00	[Label(name="must have"), Label(name="5")]	Milestone(title="DIY Site Backlog", number=1)	open
34	USER STORY: Change component published status	As **content creator**, I can **change a component published status**, so that **the component information is available to users when marked as published or hidden when it is marked as draft** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am a `Creator` user (member of the `Content Creator` group) **When** I have selected a component from a DIY Project **Then** I can toggle the published flag `Status` so that this Component from the DIY Project can be shown or hidden from viewing users. ## Tasks - [x] Task 1 - Modify the DIY Component Admin view (`ComponentInLiner`) to update the `status` field ## Story Points: 1 ## Epic: #39 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 04:17:49+00:00	2024-04-10 09:18:43+00:00	[Label(name="must have"), Label(name="1")]	Milestone(title="DIY Site Backlog", number=1)	open
35	USER STORY: Sign out	As **user**, I can **sign out**, so that **I can leave the website with security and I am no longer registered as connected ** / --- / ## Acceptance Criteria / - Acceptance Criteria 1 / **Given** that I am a `Registered` user logged in / **When** I am in any website page / **Then** I can access the sign-out web page selecting the `sign out` option in the user menu / - Acceptance Criteria 2 / **Given** that I am in the sign-out webpage / **When** I use the 'sign out' button / **Then** I become logged out the website / ## Tasks / - [x] Task 1 - Create the `sign out` option menu in the user menu in the base template / ## Story Points: / 1 / ## Epic: / #38 / ## Iteration: / [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-03-28 04:26:10+00:00	2024-04-10 14:09:08+00:00	[Label(name="must have"), Label(name="1")]	Milestone(title="DIY Site Backlog", number=1)	open
36	USER STORY: Create Development Environment	As **developer**, I can **setup the development environment**, so that **I can start developing the website** / - [x] Task 1 – Install Visual Studio Code in local environment / - [x] Task 2 – Create website Github repository and start remote environment / - [x] Task 3 – Install Django and all required libraries for runtime and development of the website / - [x] Task 4 – Create Django project and application / - [x] Task 5 - Create database in ElepantSQL servers / - [x] Task 6 - Create media storage in Cloudinary servers / - [x] Task 7 – create env.py and add all security risk keys / - [x] Task 8 - Migrate Django project to use the new database and media storage / - [x] Task 9 - Setup Heroku service for the website / - [x] Task 10 – Setup automatic deployment from Github on Heroku servers / Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1) / Points: https://github.com/Juanma1313/dys/labels/8 / Epic: https://github.com/Juanma1313/dys/issues/37	2024-04-01 11:38:01+00:00	2024-04-01 12:34:41+00:00	[Label(name="must have"), Label(name="8")]	Milestone(title="DIY Site Backlog", number=1)	open
37	EPIC: Setup initial development environment	As a **developer**, I can **setup initial environment**, so that **The website can be developed** / ###Stories / #36 / #17	2024-04-01 12:44:10+00:00	2024-04-02 07:02:29+00:00	[Label(name="must have"), Label(name="epic")]	Milestone(title="DIY Site Backlog", number=1)	open
38	EPIC: User registration	As a **user**, I can **register myself on the website**, so that **hold my information about the website ** / ### Stories / #12 / #13 / #14 / #15 / #16 / #17 / #18 / #22	2024-04-01 12:56:09+00:00	2024-04-02 07:07:05+00:00	[Label(name="must have"), Label(name="epic")]	Milestone(title="DIY Site Backlog", number=1)	open
39	EPIC: DIY Project creation and management	As a **content creator**, I can **add/modify/delete DIY projects**, so that **the DIY Projects can be published and access by users in the website** / ### User Stories / #40 / #23 / #24 / #25 / #26 / #27 / #28 / #29 / #30 / #31 / #32 / #33 / #34	2024-04-02 06:10:08+00:00	2024-04-02 07:04:38+00:00	[Label(name="must have"), Label(name="epic")]	Milestone(title="DIY Site Backlog", number=1)	open
40	USER STORY: Register users as Content Creators	As **Administrator**, I can **Give privileges to users to became Content Creators**, so that **This content creators can handle DIY projects** --- ## Acceptance Criteria - Acceptance Criteria 1 **Given** that I am an administrator **When** a user is designed as Content Creator **Then** I can assign this user to the Content Creator user group - Acceptance Criteria 2 **Given** that I am an administrator **When** a user is no longer designed as Content Creator **Then** I can revoke their Content Creator user privileges - Acceptance Criteria 3 **Given** that I am a Content Creator **When** I want to create/modify/delete a DIY Project **Then** I have sufficient privileges to perform those tasks ## Tasks - [x] Task 1 Create ` Content Creators` users group - [x] Task 2 Assign sufficient privileges to the ` Content Creators` users group - [x] Task 3 Assign designated users to the ` Content Creators` users group ## Story Points: 1+1+1 ## Epic: #37 ## Iteration: [DIY Site Backlog](https://github.com/Juanma1313/dys/milestone/1)	2024-04-02 06:59:17+00:00	2024-04-10 14:13:17+00:00	[Label(name="must have"), Label(name="3")]	Milestone(title="DIY Site Backlog", number=1)	open
41	EPIC: View DIY Projects	As a **user**, I can **access the published DIY Projects**, so that **I can follow their instructions and replicate them** / ### User Stories / #19 / #20 / #21	2024-04-02 07:17:02+00:00	2024-04-02 07:19:11+00:00	[Label(name="epic")]	Milestone(title="DIY Site Backlog", number=1)	open